## Sheet1
2301-037_Zeniya_Website_Creation
Activity | PIC |  | January 2023 | [15 empty] | February 2023 | [27 empty] | March 2023
|  |  | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Xd Design (Home) | ITP | Plan | bar: January 2023 16 to January 2023 17
Actual
Delivery to client (Home) | ITP | Plan | bar: January 2023 17
Actual
Client check design (Home) | Client | Plan | bar: January 2023 18 to January 2023 19
Actual
Client feedback (Home) | Client | Plan | bar: January 2023 19
Actual
Revise design (Home) + Design other pages | ITP | Plan | bar: January 2023 20; January 2023 23 to January 2023 26
Actual
Delivery to client (all pages) | ITP | Plan | bar: January 2023 27
Actual
Client check design (all pages) | Client | Plan | bar: January 2023 27; January 2023 30 to February 2023 2
Actual
Client feedback (all pages) | Client | Plan | bar: February 2023 3
Actual
Revise design (1rev) | ITP | Plan | bar: February 2023 6 to February 2023 7
Actual
Delivery to client (all pages 1rev) | ITP | Plan | bar: February 2023 7
Actual
Client approve design | Client | Plan | bar: February 2023 8
Actual
Front-end Development : Desktop | ITP | Plan | bar: February 2023 9 to February 2023 10; February 2023 13 to February 2023 17; February 2023 20 to February 2023 22
Actual
Front-end Development : Responsive | ITP | Plan | bar: February 2023 23 to February 2023 24; February 2023 27 to March 2023 2
Actual
Back-end Development | ITP | Plan | bar: February 2023 23 to February 2023 24; February 2023 27 to March 2023 2
Actual
1st Testing | ITP | Plan | bar: March 2023 3; March 2023 6 to March 2023 7
Actual
1st Bug Fixing (if any) | ITP | Plan | bar: March 2023 7 to March 2023 8
Actual
2nd Testing | ITP | Plan | bar: March 2023 9 to March 2023 10
Actual
2st Bug Fixing (if any) | ITP | Plan | bar: March 2023 13
Actual
3rd Testing | ITP | Plan | bar: March 2023 14
Actual
Submit the website to client | ITP | Plan | bar: March 2023 15
Actual
Client Check the website (front, back, info store) | Client | Plan | bar: March 2023 15 to March 2023 17; March 2023 20 to March 2023 21
Actual
Client feedback | Client | Plan | bar: March 2023 21
Actual